## HR Program Task Schedule
No. | Work Title | January | [30 empty] | February
|  | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | Software installation (both server & clients) | bar: January Sa 3
2 | Collect Manpower Data (manpower excel file from Ma San Moe Kyu) | bar: January Sa 10
3 | Collect Payroll Requirements (salary grade & payroll excel formula data from GM.Ma Aye Kyu Win) | bar: January Sa 10
4 | Update Software | bar: January Sa 17
5 | Fix Manpower and Payroll | bar: January Sa 17
6 | Import manpower excel data (2906 employees) | bar: January Sa 17
7 | Show Auto Download to only one staff | bar: January Sa 17
8 | New installation on database server PC | bar: January Mo 19
9 | Training for Manpower Data Entry & Manpower Data Report | bar: January Mo 19
10 | Fix and deploy software again | bar: January Fr 30
11 | Import final manpower excel data (2865 employees) | bar: January Fr 30
12 | Come for software training | bar: January Sa 31
13 | January Payroll Calculation 13.1) January Attendance Download (Auto) - Attendance records from Jan 01 to Jan 29 are automatically downloaded day by day using backdated data. - In Time, Exit Time, Late Minutes, and OT Hours were automatically generated by the software system. (Remark: When connecting 42 FP devices, the average time for one loop download is approximately 16 minutes.) | bar: February Mo 2
14 | January Payroll Calculation 14.1) Since data from Jan 30 to Jan 31 will continue to be downloaded, it will take approximately another 30 minutes. 14.2) After that, daily wages and allowances will be set according to the grade updates. 14.3) After that, payroll will be calculated according to each department and section. (Remark: Starting from tomorrow morning, the Kido team will be able to begin payroll calculation.) | bar: February Tu 3
15 | January Payroll Calculation 15.1) Attendance was collected via auto download up to the afternoon of Feb 03 (from Jan 30). 15.2) Starting from the morning of Feb 4, the Kido HR team will download attendance daily via the software using the auto download function. It has also been explained that login must be done using the auto download user account. 15.3) Before processing payroll, according to the workflow, we received the salary grade excel file provided by the Kido HR Manager and set the basic salary, attendance bonus, position bonus, and snack charges by grade. 15.4) According to the salary grade design, in order to define Skill Bonus amount by Grade and by Department, a software screen (Skill Bonus setup, by Grade by Dept) was developed, and an HR team member was assigned to enter the Skill Bonus amount at 3:40 PM in the afternoon. | bar: February Tu 3
16 | January Payroll Calculation 16.1) Starting from 9:40 AM on Feb 4, data for gatepass minutes and leave (paid leave and absent) will be entered, after which the HR Manager will proceed with payroll calculation. The payroll formulas have been developed based on requirements gathered in accordance with the Kido payroll process, so we are confident they will function correctly. (If any adjustments are required due to further discussion or alignment, the developer will make the necessary changes immediately.) 16.2) Training on how to use the software, based on the appointment date, is planned to be provided only after the payroll calculation on Feb 4 is completed. | bar: February We 4
17 | January Payroll Calculation 17.1) On February 4, we entered the January monthly gate pass data date by date, including exit time, return-in time, and final return time. (When the software runs payroll, it calculates the duration in order to deduct gate pass time accordingly.) The HR team requested that, in addition to entering gate pass data directly into the software, they would also like the option to upload the data via an Excel file, similar to manpower data entry. On Thursday, February 5, the Code-X development team will complete this update. We will provide an update on the next service visit. 17.2) Late attendance is calculated automatically during the attendance download process. Any time attendance recorded after 8:04 AM is counted as late by the system. (Although the HR team has provided the late record Excel file, data entry is not required, as with gate pass records.) 17.3) We have entered the Leave records (maternity, medical, and earned leave) provided by the HR team from the Excel file into the software. All leave records covering the period from December 2025 to February 2026 have been fully entered. (The HR team has requested that, similar to manpower data, the records be uploadable via an Excel file.) | bar: February We 4
18 | January Payroll Calculation 18.1) As the developer responsible for the Import/Export project needed to personally attend a meeting at the Customs Department on Thursday, February 5, we requested permission from the Kido GM on Wednesday, February 4. 18.2) In addition to allowing gate pass entry directly in the software, the Code-X development team is developing today the functionality to upload gate pass data via an Excel file, similar to manpower data entry. Next time, as we have already reached the payroll run stage, payroll calculation will be carried out. | bar: February Th 5
19 | January Payroll Calculation 19.1) Employees (new manpower) hired after January 31 will be entered into the software by the Kido HR team staff before payroll calculation. (Data will be imported via Excel.) 19.2) The fingerprint late data has been imported into the software using Excel import. 19.3) Resigned employees from the manpower list are also entered into the software by the Kido HR team staff before payroll calculation. (This is done to ensure that manpower updates are completed before payroll processing. Starting from February 7, we kindly request that all employee joiner and leaver records be consistently entered into the software.) 19.4) To enable payroll calculation, the Kido HR team staff has made grade changes for the manpower in the A1 section. 19.5) Payroll has been calculated for the A1 section. - When calculating payroll for the A1 section, the payroll is correct for employees who have no leave days. - When calculating position bonus/skill and snack charges, if there are leave days, the calculation is currently based only on actual attendance days. However, since public holidays and off days should also be included to determine the actual days, this needs to be developed by the Code-X team. 19.6) Requirements by Kido HR Manager - The grade column needs to be displayed on the payroll screen. - To provide a Quick View that allows the salary grade screen to be viewed directly within the payroll section. | bar: February Fr 6
20 | The Code-X development team will develop the requested requirements from Kido HR team on February 7. Payroll Calculation for other sections will be continued on February 9 (Monday). | bar: February Sa 7
21 | Request from Code-X 21.1) We request the Kido HR team to update the grades for the manpower to be ready Payroll Calculation.
22 | HR Manager Ma San Moe Kyu & Ma Phyo Sandar Kyaw - - Payroll calculation (salary calculation) and how to export it to Excel were explained/ provided during the training. Ma Phyo Sandar Kyaw - 1) Please keep it enabled to download attendance every morning using the auto-download user account. 2) How to check daily attendance: 2.1) No check-in entries 2.2) No check-out entries 2.3) Absent cases with no check-in and no check-out 2.4) Approved leave days 2.5) Monthly / Daily / Weekly views 2.6) How to maintain check-in, check-out, and absent records Training was provided and explained. 3) The female security staff are required to attend from 7:30 AM to 4:40 PM, so a shift type has been assigned. Since they start at 7:30 AM, 0.5 OT hour has been recorded as a requirement. It will be developed and fixed by Code-X development team. 4) Since the male security staff have a working hour of 9 hours, 1 hour of OT should be given, and after completing a full week of the schedule, 4 hours of OT for the last day of the week should be added. This requirement was taken from Ma Phyo Sandar Kyaw. 5) The male security staff follow assigned shifts instead of regular hours, so it was explained that a duty roster needs to be prepared. Since the schedule for the whole month of February is ready, the February shift assignments were provided, and those receiving training were also allowed to take a break at the same time. Ma Su Su Wai - 1) How to enter leave in the Leave Form, and how to review it according to date range and type of leave. 2) How to check the total leave days taken according to the type of leave. Training was provided and explained. Ma Chaw Su - 1) Since she has been updating new manpower in the software via Excel import since February 6, including adding new employees and processing resignations, there is no need to provide it again. Ma Chaw Su - | bar: February Mo 9
23 | Code-X development team will develop the requested requirements from Kido HR Team. | bar: February Tu 10